## Project Timeline
Underwater ROV Manipulator: Project Timeline
PROJECT TITLE |  | Underwater ROV Manipulator
CLIENT |  | Geoffrey Hollinger
GROUP |  | Underwater ROV Manipulator
WBS NUMBER | TASK TITLE | TASK OWNER | START WEEK | END WEEK | DUE DATE | DURATION IN WEEKS
1 | Reasearch |  | 0 | 5 |  | 5
1.1 | Project Timeline | Zack | 2 | 3 | 2019-10-17 | 1
1.2 | Team Protocols and Standards | - | 2 | 3 | 2019-10-17 | 1
1.3 | Engineering Requirements Draft | - | 2 | 3 | 2019-10-17 | 1
1.5 | Team/Project Google Site | Zack | 3 | 4 | 2019-10-24 | 1
1.6 | Start-Up Packet | Zack | 3 | 4 | 2019-10-24 | 1
1.7 | Block Diagram Draft | Stephen | 4 | 5 | 2019-10-31 | 1
1.9 | Engineering Requirements | - | 2 | 8 | 2019-11-28 | 6
1.11 | Block Diagram | Stephen | 4 | 9 | 2019-12-05 | 5
1.12 | Power Budget | Steven | 8 | 9 | 2019-12-05 | 1
1.13 | BOM | Stephen | 8 | 9 | 2019-12-05 | 1
2 | Prototyping |  | 5 | 12 |  | 7
2.1.1 | On Board Control Software Block | Zack | 5 | 7 | 2019-12-05 | 2
2.1.2 | On Board Control Hardware Block | Stephen | 5 | 7 | 2020-01-06 | 2
2.2 | Manipulator Block | Zack | 9 | 10 | 2020-02-05 | 1
2.3 | Computer Vision Block | Stephen | 5 | 7 | 2020-01-06 | 2
2.4 | Sensors Block | Stephen | 7 | 10 | 2020-02-10 | 3
2.5 | Lights Block | Stephen | 7 | 10 | 2020-02-10 | 3
2.6 | Shore Control Block | Stephen | 5 | 7 | 2020-01-06 | 2
2.7 | Movement Block | Steven | 9 | 10 | 2020-02-05 | 1
2.8 | Power Block | Steven | 5 | 7 | 2019-12-05 | 2
2.9 | Enclosure Block | Stephen | 9 | 10 | 2020-01-06 | 1
| ROS (Zack) | Zack | 5 | 8 |  | 3
| Arduino (Stephen) | Stephen | 5 | 9 |  | 4
| Power (Steven) | Steven | 5 | 12 |  | 7
| Control Station (Stephen) | Stephen | 9 | 12 |  | 3
| Manipulator (Zack) | Zack | 9 | 12 |  | 3
3 | Testing |  | 12 | 17 |  | 5
3.1 | First Block Check-Off | - |  |  | 2020-01-20 | 0
3.2 | Design Review | - |  |  | 2020-01-27 | 0
3.3 | All Block Check-Off | - |  |  | 2020-02-10 | 0
3.4 | System Review 1 | - |  |  | 2020-03-02 | 0
3.5 | System Review 2 | - |  |  | 2020-04-20 | 0
4 | Final Assembly |  | 17 | 22 |  | 5
4.1 | Project Summary Video | - |  |  | 2020-05-15 | 0
4.2 | Elevator Speech | - |  |  | 2020-05-15 | 0
4.3 | Project Closeout Packet | - |  |  | 2020-05-15 | 0
4.4 | Poster Draft | - |  |  | 2020-05-08 | 0
4.5 | Poster | - |  |  | 2020-05-15 | 0
4.6 | Engineering Expo | - |  |  | 2020-05-15 | 0
5 | Final Testing |  | 22 | 27 |  | 5
4.1 | Project Summary Video | - | 25 | 26 | 2020-05-15 | 1
4.2 | Elevator Speech | - | 26 | 27 | 2020-05-15 | 1
4.3 | Project Closeout Packet | - | 26 | 27 | 2020-05-15 | 1
4.4 | Poster Draft | - | 20 | 21 | 2020-05-08 | 1
4.5 | Poster | - | 25 | 26 | 2020-05-15 | 1
4.6 | Engineering Expo | - | 26 | 27 | 2020-05-15 | 1

## Gantt Chart
Underwater ROV Manipulator: Project Timeline
PROJECT TITLE |  | Underwater ROV Manipulator | [6 empty] | COMPANY NAME | Group 44
PROJECT MANAGER |  | Geoffrey Hollinger | [6 empty] | DATE | 2019-10-04
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | END DATE | DUE DATE | START ON DAY | DURATION IN DAYS | PERCENT OF TASK COMPLETE
1 | Initial Project Development
1.1 | Project Timeline | Zack | 2019-10-08 | 2019-10-10 | 2019-10-17 | 0 | 2 | 25%
1.2 | Team Protocols and Standards | - | 2019-10-08 | 2019-10-10 | 2019-10-17 | 0 | 2 | 100%
1.3 | Engineering Requirements Draft | - | 2019-10-14 | 2019-10-15 | 2019-10-17 | 6 | 1 | 90%
1.4 | Client Update (1) | - | 2019-10-15 | 2019-10-17 | 2019-10-24 | 7 | 2 | 0%
1.5 | Team/Project Google Site | Zack | 2019-10-15 | 2019-10-17 | 2019-10-24 | 7 | 2 | 25%
1.6 | Start-Up Packet | Zack | 2019-10-15 | 2019-10-17 | 2019-10-24 | 7 | 2 | 0%
1.7 | Block Diagram Draft | Stephen | 2019-10-22 | 2019-10-25 | 2019-10-31 | 14 | 3 | 0%
1.8 | Client Update (2) | - | 2019-11-12 | 2019-11-14 | 2019-11-21 | 35 | 2 | 0%
1.9 | Engineering Requirements | - | 2019-11-19 | 2019-11-20 | 2019-11-28 | 42 | 1 | 80%
1.1 | Client Update (3) | - | 2019-11-26 | 2019-11-28 | 2019-12-05 | 49 | 2 | 0%
1.11 | Block Diagram | Stephen | 2019-11-26 | 2019-11-27 | 2019-12-05 | 49 | 1 | 0%
1.12 | Power Budget | Steven | 2019-11-26 | 2019-11-28 | 2019-12-05 | 49 | 2 | 0%
1.13 | BOM | Stephen | 2019-11-26 | 2019-11-29 | 2019-12-05 | 49 | 3 | 0%
2 | Advanced Research and Building Phase
2.1.1 | On Board Control Software Block | Zack | 2019-10-15 |  | 2019-12-05 |  |  | 0%
2.1.2 | On Board Control Hardware Block | Stephen | 2019-10-15 |  | 2020-01-06 |  |  | 0%
2.2 | Manipulator Block | Zack | 2019-12-05 |  | 2020-02-05 |  |  | 0%
2.3 | Computer Vision Block | Stephen | 2019-10-15 |  | 2020-01-06 |  |  | 0%
2.4 | Sensors Block | Stephen | 2019-11-15 |  | 2020-02-10 |  |  | 0%
2.5 | Lights Block | Stephen | 2019-11-15 |  | 2020-02-10 |  |  | 0%
2.6 | Shore Control Block | Stephen | 2019-10-15 |  | 2020-01-06 |  |  | 0%
2.7 | Movement Block | Steven | 2019-12-05 |  | 2020-02-05 |  |  | 0%
2.8 | Power Block | Steven | 2019-10-15 |  | 2019-12-05 |  |  | 0%
2.9 | Enclosure Block | Stephen | 2019-12-05 |  | 2020-01-06 |  |  | 0%
3 | Testing Phase
3.1 | First Block Check-Off | - |  |  | 2020-01-20 |  |  | 0%
3.2 | Design Review | - |  |  | 2020-01-27 |  |  | 0%
3.3 | All Block Check-Off | - |  |  | 2020-02-10 |  |  | 0%
3.4 | System Review 1 | - |  |  | 2020-03-02 |  |  | 0%
3.5 | System Review 2 | - |  |  | 2020-04-20 |  |  | 0%
4 | Presentation Phase
4.1 | Project Summary Video | - |  |  | 2020-05-15 |  |  | 0%
4.2 | Elevator Speech | - |  |  | 2020-05-15 |  |  | 0%
4.3 | Project Closeout Packet | - |  |  | 2020-05-15 |  |  | 0%
4.4 | Poster Draft | - |  |  | 2020-05-08 |  |  | 0%
4.5 | Poster | - |  |  | 2020-05-15 |  |  | 0%
4.6 | Engineering Expo | - |  |  | 2020-05-15 |  |  | 0%