## Gantt Chart
Bird Foraging Puzzle Project
Team Members: Michael Crockett, Shengmei Hu, Brieanna Jeibmann, Bradley Marin | [6 empty] | Project Partner: |  | Jamie Cornelius
TASK TITLE | TASK OWNER | START DATE | DUE DATE | STATUS | Fall Term |  |  |  | Winter Term |  |  | Spring Term
[5 empty] | Month 1 | Month 2 |  | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9
Problem Definition
Contact Project Partner | Team | 2021-10-06 | 2021-10-12 | Complete
Research Project Topics | Team | 2021-10-06 | N/A | Complete
Section 1 Documents | Team | 2021-10-08 | 2021-10-22 | Complete
Preliminary Design
Section 2 Documents | Team | 2021-10-15 | 2021-10-29 | Complete
Create Project Requirements | Team | 2021-10-15 | 2021-10-29 | Complete
Design Concept Research | Team Individually | 2021-10-10 | 2021-12-03 | Complete
Section 3 Document | Team | 2021-11-05 | 2021-11-19 | Complete
Build Proof of Concept (Tech demo) | Team | 2021-11-05 | 2021-12-03 | Complete
Modular Testing
Indivdual Block 1 Construction | Team Individually | 2022-01-03 | 2022-02-27 | Complete
Indivdual Block 1 Verification | Team Individually | 2022-02-28 | 2022-03-01 | Complete
Indivdual Block 2 Construction | Team Individually | 2022-01-03 | 2022-03-13 | Complete
Indivdual Block 2 Verification | Team Individually | 2022-03-14 | 2022-03-15 | Complete
System Level Testing
Connect blocks to full System | Team | 2022-04-01 | 2022-04-15 | Complete
Full System Adjustments and Final | Team | 2022-04-15 | 2022-05-01 | Complete
Full System Verification | Team | 2022-05-02 | 2022-05-04 | Complete
Presentation Preperation
Create Poster | Team | 2022-04-01 | 2022-05-13 | Complete
Poster Presentation | Team | 2022-06-03 | 2022-06-03 | Complete
Project Closing
Final Documentation | Team | 2022-04-01 | 2022-05-06 | Complete
Closing Tasks | Team | 2022-05-03 | 2022-05-06 | Complete